## Minutes
PROJECT REVIEW — MINUTES
Date: | 2026-04-09 |  | Chair: | R. Kumar
Present: | A. Menon, L. Wei, O. Haddad
Discussion
Action | Owner | Due | Status
Finalise vendor shortlist | A. Menon | 2026-04-16 | Open
Circulate revised budget | L. Wei | 2026-04-12 | Done
Book site visit | O. Haddad | 2026-04-20 | Open